## Daily Report
Daily Production Report
Free template from iFILMthings.com. Fill the yellow cells. Totals, to-date figures and cast hours work themselves out.
Production |  |  |  |  | Date
Shoot day |  |  |  |  | Report no.
Director |  |  |  |  | Producer
1st AD |  |  |  |  | DP
Location(s) |  |  |  |  | Weather
TIMES
Crew call | Shooting call | First shot | Lunch out | Lunch in | Second meal | Scheduled wrap | Camera wrap | Last person out | Camera over by
SCENES SHOT TODAY
Scene | Set and description | Pages | Setups | Screen min | Status |  |  |  | Notes
Status: Done, Part or Not shot. Pages in eighths: type 1 6/8. Screen time in minutes: 1.5 = 1 min 30 sec.
PROGRESS
|  | Script total | Before today | Today | To date | Remaining
Scenes (done)
Pages
Screen time (min)
Setups
Scenes scheduled |  |  |  |  | Part completed
Not shot (moved) |  |  |  |  | Added or retakes
Crew count |  |  |  |  | Extras
Camera cards |  |  |  |  | Sound rolls
Backups |  |  |  |  | Meal penalties
Crew overtime
CAST TIMES
# | Character | Performer | Status | Call | On set | Meal out | Meal in | Wrap | Hours (less meal)
Status: SW start work, W work, WF work finish, SWF start work finish, H hold, T travel, R rehearse
NOTES AND SIGN-OFF
Delays and why
Scenes not finished
Injuries or incidents
Equipment and damage
Other notes
Prepared by
Approved by

## Example (Dead Air Day 1)
Daily Production Report: Dead Air, Day 1 (example)
Free template from iFILMthings.com. Fill the yellow cells. Totals, to-date figures and cast hours work themselves out.
Production | Dead Air (short film) |  |  |  | Date | Mon 13 Oct
Shoot day | 1 of 3 (+1 reserve) |  |  |  | Report no. | 1
Director | Alex Rivera |  |  |  | Producer | Jo Kim
1st AD | Priya Shah |  |  |  | DP | Lena Park
Location(s) | Nora's apartment, 4 Elm Court |  |  |  | Weather | Clear, 52F. Sunrise 7:12 AM
TIMES
Crew call | Shooting call | First shot | Lunch out | Lunch in | Second meal | Scheduled wrap | Camera wrap | Last person out | Camera over by
5:30 | 6:30 | 6:52 | 12:00 | 12:30 | None | 17:30 | 17:40 | 18:25
SCENES SHOT TODAY
Scene | Set and description | Pages | Setups | Screen min | Status |  |  |  | Notes
11 | EXT APARTMENT BUILDING, dawn | 0.375 | 3 | 0.42 | Done |  |  |  | Sunrise, 20 min to spare
1 | INT NORA'S APARTMENT, day | 0.625 | 4 | 0.67 | Done
10 | INT NORA'S APARTMENT, night | 1.75 | 7 | 1.83 | Part |  |  |  | Last 2/8 moves to Thu 16
Status: Done, Part or Not shot. Pages in eighths: type 1 6/8. Screen time in minutes: 1.5 = 1 min 30 sec.
PROGRESS
|  | Script total | Before today | Today | To date | Remaining
Scenes (done) |  | 11 | 0
Pages |  | 13.375 | 0
Screen time (min) |  | 14 | 0
Setups |  | 86 | 0
Scenes scheduled | 11, 1, 10 |  |  |  | Part completed | 10 (1 6/8 of 2 pages)
Not shot (moved) | None |  |  |  | Added or retakes | None
Crew count | 14 |  |  |  | Extras | 0
Camera cards | A001 to A006, 604 GB |  |  |  | Sound rolls | S001, 41 files
Backups | 2 copies, checksums OK. Shuttle drive to editor 7 PM |  |  |  | Meal penalties | None
Crew overtime | Camera, grip and electric: 10 min
CAST TIMES
# | Character | Performer | Status | Call | On set | Meal out | Meal in | Wrap | Hours (less meal)
1 | NORA | Jess Monroe | SW | 5:30 | 6:30 | 12:00 | 12:30 | 17:45
2 | EDDIE | Tom Achebe | SW | 10:00 | 11:00 | 12:00 | 12:30 | 17:45
Status: SW start work, W work, WF work finish, SWF start work finish, H hold, T travel, R rehearse
NOTES AND SIGN-OFF
Delays and why | Window blackout took 40 min longer than planned (6 windows, not 4). Sc 10 started at 1:10 PM, not 12:30 PM.
Scenes not finished | Sc 10, last 2/8 page (Eddie leaves): moved to the reserve day, Thu 16 Oct, same apartment. Jess and Tom on hold.
Injuries or incidents | None.
Equipment and damage | One LED panel failed at 2 PM. Swapped for the spare. Return to the rental house for a credit.
Other notes | Sunrise shot made with 20 minutes to spare. Neighbor noise complaint at 3 PM, settled by the producer. No meal penalties.
Prepared by | Priya Shah, 1st AD
Approved by | Jo Kim, Producer